GREGGO & FERRARA, INC.

CHURCHMANS ROAD & SR7 INTERCHANGE REHAB OF BRIDGES 716, 716A, & 717 I-95 OVER SR7

CONTRACT 91-101-04/96-074-02

TWO WEEK CONSTRUCTION SCHEDULE

FOR THE WEEK BEGINNING MONDAY, 3/22/99 TO MONDAY, 4/5/99

| ACTIVITY |  |  |  | LOCATION |  |  |  |  | M |  | T | W | T | F |  | S | S |  |  | M | T | W | T |  |  | F | S | S |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Abutment Construction |  |  |  | Abutment A NBR and Wingwall B |  |  |  |  | X |  | X | X | X | X |  | X |  |  |  | X | X | X | X |  |  |  |  |  |  |
| MSE Wall Construction |  |  |  | MSE Walls A & B |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| MSE Wall Construction |  |  |  | MSE Wall C & D |  |  |  |  | X |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Moment Slab |  |  |  | MSE Walls A and/or B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| Embankment |  |  |  | SR7, North and South of Churchmans Rd. |  |  |  |  | X |  | X | X | X | X |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| Curb Installation |  |  |  | Ramp B |  |  |  |  | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Storm Drainage Structures |  |  |  | Various Locations |  |  |  |  | X |  | X | X | X | X |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| BCBC/Type B Hotmix Paving |  |  |  | WB Churchmans Rd., Church. Pl. to West End |  |  |  |  | X |  | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Lighting Cable, Standards, & Load Centers |  |  |  | Various Locations |  |  |  |  | ? |  | ? | ? | ? | ? |  |  |  |  |  | ? | ? | ? | ? |  |  |  |  |  |  |
| Type B Hotmix Paving |  |  |  | WB Churchmans Rd. in front of Abutment B |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guardrail Installation |  |  |  | WB Churchmans Rd. from Abutment B to 12+085 |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PCC Barrier Relocation |  |  |  | WB Churchmans Road |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Loop Detector Installation |  |  |  | WB Churchmans Road |  |  |  |  |  |  | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Shift Traffic into Stage III/Ph. 2 Configuration |  |  |  | WB Churchmans Rd., Tech Rd. to West End |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Shift Traffic into Stage III/Ph. 2 Configuration |  |  |  | EB Churchmans Rd., SR7 to Tech Rd. |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Excavation/GABC |  |  |  | EB Churchmans Rd., Tech Road to East End |  |  |  |  | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Curb Installation |  |  |  | EB Churchmans Rd., Tech Road to East End |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| Excavation/GABC |  |  |  | EB Churchmans Rd., SR7 to Tech Road |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| Sign Structure Foundation Construction |  |  |  | OH-1 Rt., C-2, C-5, and C-6 |  |  |  |  | X |  | X | X | X | X |  |  |  |  |  | X | X | X | X |  |  |  |  |  |  |
| Notes/Legend: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Rmuir |  |  |  |  |  |  |  |  |  |  |
| 1) All work is weather permitting and highly dependent upon grade conditions. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Project Manager |  |  |  |  |  |  |  |  |  |  |
| Hotmix Activities |  | Nightwork |  |  | Concrete Pour |  | Good Friday |  |  |  |  |  |  |  | Greggo & Ferrara, Inc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

GREGGO & FERRARA, INC.

CHURCHMANS ROAD & SR7 INTERCHANGE REHAB OF BRIDGES 716, 716A, & 717 I-95 OVER SR7

CONTRACT 91-101-04/96-074-02

TWO WEEK SCHEDULE

FOR THE WEEK BEGINNING MONDAY, 10/11/99 TO MONDAY, 10/25/99

| ACTIVITY | LOCATION | M | T | W | T | F | S | S | M | T | W | T | F | S | S |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Form Removal and Misc. Cleanup/Finishing | NB SR7 Bridge over Churchmans Rd./Wall B | X | X | X | X | X |  |  | X | X | X | X | X |  |  |
| Bridge Deck Construction | SB SR7 Bridge over Churchmans Rd. | X | X | X | X | X |  |  | X | X | X | X |  |  |  |
| Type B Hotmix Paving | Churchmans Road | X | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Type B Hotmix Paving | SB SR7 Frontage Rd. thru SR4 |  |  |  | X |  |  |  |  |  |  |  |  |  |  |
| Signal Head Inst./Adjust. & Loop Detector Inst. | Churchmans Rd. Intersections |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Realigning Traffic to Final Configuration | Churchmans Road |  | X | X | X |  |  |  |  |  |  |  |  |  |  |
| Safety Barrier | MSE Wall A |  |  |  | X | X |  |  |  |  |  |  |  |  |  |
| Light Poles and Wiring | NB SR7, South End Thru Churchmans Rd. |  |  |  |  |  |  |  | X | X | X |  |  |  |  |
| Pole Base, Conduit, Wire, and Light Pole Inst. | SB SR7, SR4 to North End and other locations |  |  |  |  |  |  |  |  |  | X | X | X |  |  |
| Guardrail and Impact Attenuator Installation | Churchmans Rd. Median |  |  |  |  |  |  |  | X | X | X | X | X |  |  |
| Sign Foundations | GM-9 |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Sign Installation | All avail. signage required for NB SR7 Opening | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Opening New Roadway to Traffic | NB SR7 and Ramps B/B-1/C/C-1 | X |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PCC Barrier Relocation | Ramps A/D and NB/SB SSR7 | X | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Remove Hotmix Crossovers | SR7 Med. & SB Roadways @ North & South Ends |  | X | X | X | X |  |  | X | X | X | X | X |  |  |
| Complete Embankment | SB SR7, North of Churchmans Rd. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| PCC Removal | SB SR7, South End Tie-in |  |  | X | X | X |  |  |  |  |  |  |  |  |  |
| Complete MSE Wall | MSE Wall A |  |  |  |  |  |  |  | X | X | X | X | X |  |  |

Notes/Legend:

- All work is weather permitting.

- All hotmix paving operations are contingent upon plant and crew availability.

- New Road Opening includes relocating PCC Barrier and pavement striping.

- Placing Traffic into Final Configuration includes temporary striping placed according to final striping pattern shown on the plans.

Rmuir

Project Manager

Greggo & Ferrara, Inc.

| Night Work | X |
| --- | --- |

| Night Paving 8PM to 6AM | X | Deck Pour | Road Opening |
| --- | --- | --- | --- |

GREGGO & FERRARA, INC.

DMB Contract No. 578

West Approach Repaving and Modifications

Landers Lane to DMB

THREE-WEEK SCHEDULE

| FOR THE PERIOD BEGINNING 4/16/01 TO 5/7/01 |  |  |  |  |  |  |  |  | APRIL |  |  |  |  |  |  |  |  |  |  |  | MAY |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 16 | 17 | 18 | 19 | 20 | 21 | 22 |  | 23 |  | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 |
| ACTIVITY | LOCATION | M | T | W | T | F | S | S |  | M |  | T | W | T | F | S | S | M | T | W | T | F | S | S |
| Relocating Temp. Barrier | SB I-295/Toll Plaza/Ramps A-D | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |
| Relocating Temp. Barrier | SB I-295, Stage V(B) | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Jersey Barrier | SB I-295 @ Pier 4 |  |  |  | X | X | X |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Guiderail Removal | SB I-295, Shldr. & Ramp D |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Construct New Service Road (4) | Ramp LN-8 | X | X | X | X | X |  |  |  | X |  | X | X | X | X |  |  | X | X | X | X | X |  |  |
| Replace Toll Lanes | Toll Lanes 4 & 5 |  | X | X | X | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Replace Toll Lanes | Toll Lanes 6 & 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X |  |  |  |
| Widening/Reconstruction | SB I-295 Shldr. |  | X | X | X | X | X |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Hotmix Overlay | SB I-295 Lanes 7, 8, & Shldr. |  |  | X | X | X | X |  |  | X |  | X | X | X | X | X |  |  |  |  |  |  |  |  |
| Final Striping, Polyurea | NB I-295 & Ramps E - H |  |  |  |  |  |  |  |  | X |  | X |  |  |  |  |  |  |  |  |  |  |  |  |
| Reconstructing Ramps (3) | Ramp D |  | X | X | X | X | X |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reconstructing Ramps (3) | Ramp B |  |  |  |  |  |  |  |  | X |  | X | X | X | X | X |  |  |  |  |  |  |  |  |
| Reconstructing Ramps (3) | Ramp A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X | X | X | X |  |
| Relocating Temp. Barrier | SB I-295, Stage VI(B) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X |  |  |  |  |  |
| PCC Pavement Removal | DE9 Median, Roadway |  |  |  |  |  |  |  |  | X |  | X | X | X | X |  |  |  |  |  |  |  |  |  |
| Excavation/GABC | DE9 Median, Roadway |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  | X | X |  |  |  |  |  |
| Hotmix Paving, Base | DE9 Median, Roadway |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | X | X |  |  |
| Backwall Reconstruction | NB & SB DE9 over I-295, Med. | X | X | X | X | X |  |  |  | X |  | X | X | X | X |  |  | X | X | X | X | X |  |  |
| Demo/Patch Ex. 8' Median | NB & SB DE9 over I-295 | X | X | X | X | X |  |  |  | X |  | X | X | X | X |  |  | X | X | X | X | X |  |  |

Notes/Legend:

- All work is weather and/or temperature permitting.

- Hotmix Paving is dependent upon crew and plant availability.

| 3) | Ramp Reconstruction includes patching PCC pavement, excavation, GABC, u'drain, and hotmix paving. |  |  |  | Rmuri |
| --- | --- | --- | --- | --- | --- |
|  | MOT for Ramp Reconstruction includes full closure and detour of traffic during construction. |  |  |  |  |
| 4) | New Service Road Ramp LN-8 construction includes slope stabilization using Gabions and Reno Mattresses. |  |  |  | Project Manager |
|  | Night work requiring lane closures | X | Hotmix Paving | X | Greggo & Ferrara, Inc. |

Revising or Modifying

- necessary reaction to change

- modify logic to reflect work plan

- internal or external pressure to accelerate or regain lost time