Almost Heaven Habitat for Humanity

At-A-Glance Women Build Building Construction Schedule

| Project | Date | Primary Activities of the Day | Minimum # of |
| --- | --- | --- | --- |
| Day |  |  | volunteers |
| Pre-Build | Monday, November 8th | Ground Breaking Ceremony | All are |
|  |  |  | Welcome |
|  | November 2010 thru |  | Skilled |
| Pre-Build |  | Excavation and Foundation Work | Volunteers |
|  | March 2011 |  |  |
|  |  |  | Only |
| Wall Raising | Saturday, March 5th | We will raise the interior and exterior | 20 |
|  |  | walls of the house |  |
|  | March 7th – 12th | Finish up the framing, Set roof trusses, |  |
| Build Week # 1 |  | Start roofing | 20 |
|  | March 14th – 19th | Finish roofing, Install windows and |  |
| Build Week # 2 |  | doors, start Rough-in Plumbing and | 20 |
|  |  | Electric |  |
|  | March 21st – 26th | Install vinyl siding, soffit, and fascia, |  |
| Build Week # 3 |  | Complete porches, Finish Rough-in | 20 |
|  |  | Plumbing and Electric |  |
| Build Week # 4 | March 28th – | Finish all remaining exterior work, | 20 |
|  | April 2nd | Finish all Drywall prep |  |
| Build Week # 5 | April 4th – 9th | Drywall Week | 20 |
| Build Week # 6 | April 11th – 16th | Insulation, Landscaping, Painting | 20 |
| Build Week # 7 | April 18th – 23rd | Flooring, Trim, Fixtures | 20 |
|  | April 25th – 30th | Cabinets, Trim, Finishing Plumbing, |  |
| Build Week # 8 |  | Electric, and HVAC | 20 |
| Build Week # 9 | May 2nd – 6th | Punch List | 20 |
| House Blessing | Saturday, May 7th | We will dedicate the house and turn the | All are |
|  |  | keys over to Laura Blevins | Welcome |

Almost Heaven Habitat for Humanity

At-A-Glance Women Build Building Construction Schedule

This schedule is subject to change based weather or other unexpected delays.

Female volunteers of all ages and skill levels will be needed. Groups, families and individuals are also welcome! Men are also welcome, but they will be asked to

serve as a hands-on helper or in a non-construction role.

If you would like to volunteer to work on one or more of these build days, please call ahead to let us know that you are coming so we can plan accordingly. This will allow us to better plan for the number of volunteers each build day. Like any good party we’d like to know how many guests to expect so we don’t run short on fun or party favors (in this case tools and building materials). We anticipate some of the build days will fill up.

In the event that the build day is ‘full’ we work to find another day that works for you.

Each volunteer will need to complete a set of paperwork prior to being able to build on the site. Youth under the age of 18 must have their paperwork completed by a parent or legal guardian. Youth under the age of 10 must be accompanied by their parent or guardian.

You are welcome to bring your own tools, however we supply all necessary tools for the build. Please call in advance to discuss the use of pneumatic tools as they are generally not allowed on our construction sites when unskilled volunteers are present.

We work from 9 am until 4 pm with ½ hour for lunch. Lunch is not provided unless otherwise specified so please plan to pack a lunch. We plan to work rain or shine.

Directions to the build site are available upon request.

Questions?

Call Rose McFarlane at 304.358.7642 or email volunteer@almostheavenhabitat.org