## PROCUREMENT SCHEDULE
SH16 PROCUREMENT SCHEDULE
|  | Cell Key |  |  | Line Key | [16 empty] | Last Updated: | 31/02/2014
|  | Requires Attention |  |  | Tender issued awaiting response | [16 empty] | By Whom: | Greg Arnold
|  | Requires Urgent Attention |  |  | Response Received, awaiting evaulation
|  | Scheduled Date Not Met |  |  | Closed Out
|  | Awaiting Package Information |  |  | Contract Not Required
Package No. | Items / Works to Procure | Contract Type | Resp. Person | Delegated to | Discipline | Tender Package Complete & Issued |  | Tender Period | Prices Received |  | Review Prices and Award Contract |  |  | Lead Time |  |  | Date Required on Site |  | Supplier / Contractor | Contract / Agreement Number | Signed Agreement Returned | Insurances | Warranties | Comments
|  | eg Works, Minor Works, Supply, Plant Hire |  |  |  | Scheduled Date | Actual | Duration Required | Scheduled Date | Actual | Duration Required | Scheduled Date | Actual | Duration Required | Scheduled Delivery | Actual | Scheduled | Actual
29 | Streetlighting - Temp Relocation | Minor Works | HC |  | Early Works | [11 empty] | 2014-01-14 | [6 empty] | Done ad hoc
32 | Electrical/ITS | Works | HC |  | Services | [11 empty] | 2013-01-14 | [6 empty] | Steve Newbury
44 | Structural Steel Supply - TL5 Barrier Rail | Supply | TS |  | Structures | 2014-02-07 |  | 2w | 2014-02-21 |  | 1w | 2014-02-28 |  | 3m | 2014-05-31 |  | 2014-05-31 | [6 empty] | Scope. Hornell, Crusader, Sable Engineering, North Shore Plate Cutting
68 | Pavement Aggregate Supply | Supply | ME |  | Earthworks | [11 empty] | 2013-09-13 |  | TBC |  |  |  |  | ME & HM - Awaiting Spec. - 2wks
90 | Anti-Graffiti Painting | Works | TS | JL | Finishing | 2014-01-17 |  | 2w | 2014-01-31 |  | 1w | 2014-02-07 |  | 3w | 2014-02-28 |  | 2014-02-28 | [6 empty] | Cake Commercial, Graffiti Solutions - AE's to forward Spec. & locations to GA
75 | Supply Retaining Wall Components RW3 and RW7 | Supply | HM | AM | Structures | [11 empty] | 2014-01-13 | [6 empty] | stone strong self perform / ICB design build
126 | Filter Treatment Devices | Supply | [21 empty] | Stormwater 360
128 | Steel Temporary Barrier installation | Works | HM | HM | [19 empty] | Tom Ryan Cartage
129 | Walkway lighting - Install Lights/Pits & Draw Cables | Works | AS | SN | [19 empty] | North Power
50 | Expansion Joint Supply | Supply | TS | JL | Structures | 2014-01-30 |  | 2w | 2014-02-13 |  | 1w | 2014-02-20 |  | 12w | 2014-05-15 |  | 2014-05-15 | [6 empty] | Nuralite (WABO),
55 | Concrete Placement | Works | TS | JL | Structures | 2014-03-17 |  | 2w | 2014-03-31 |  | 1w | 2014-04-07 |  | 2w | 2014-04-21 |  | 2014-04-21 | [6 empty] | Conset Construction, VJ Concrete, Brewis Concrete
72 | Asphalt Pavement | Works | HM |  | Earthworks | [11 empty] | 2014-02-24
73 | Asphalt Milling/Profiling | Works | HM |  | Earthworks | [11 empty] | 2014-03-03
74 | Linemarking | Works | AS | NO | Finishing | [10 empty] | HC
77 | Drainage Installation (if not self proformed) | Works |  |  | Earthworks
21 | Supply of Precast Concrete Pipes/Culverts/Endwalls/Manholes | Supply | AS | HC | Early Works | [11 empty] | 2013-09-02 | [6 empty] | Hynds
46 | Precast Pre-Stressed Concrete Supply - includes delivery | Supply | TS |  | Structures | 2013-11-14 |  | 2w | 2013-11-28 | 2013-11-08 | 2w | 2013-12-12 |  | 3m | 2014-03-14 |  | 2014-03-14 | [6 empty] | Stahlton, Concrete Structures, Stresscrete
47 | Precast Concrete Supply - includes delivery | Supply | TS |  | Structures | 2013-11-21 |  | 2w | 2013-12-05 | 2013-11-08 | 1w | 2013-12-12 |  | 3m | 2014-03-14 |  | 2014-03-14 | [6 empty] | Stahlton, Concrete Structures, Stresscrete, Wilco, Wilson
60 | Pavement Strip Drain Supply | Supply | HC |  | Earthworks | [11 empty] | 2013-09-13 | [6 empty] | Date required TBC. ACO
62 | Causeway Ground Improvements - CFA Piling | Works | ME |  | Earthworks | [11 empty] | 2013-09-13 | [6 empty] | FH, Brian Perrys, Spiral Drillers, Hauraki Piling. --> VO to BP. ME to compile special conditions
54 | Concrete & Asphalt Cutting/Coring/Drilling | Works | TS |  | Structures | 2013-12-09 |  | 2w | 2013-12-23 | 2013-11-08 | 2w | 2014-01-06 |  | 1w | 2014-01-13 |  | 2014-01-13 | [6 empty] | A1 Kiwi Cutters, Lowery --> All let
1 | Ground Investigation - Geotechnical Drilling | Minor Works | AS |  | Investigation |  |  |  |  | 2012-11-21 |  | 2012-11-23 | [6 empty] | McMillans Drilling | 9500712 | Yes | Yes |  | Contracts in place
2 | Ground Service Locator | Minor Works | AS |  | Investigation | [13 empty] | Underground Service Locators | 9500594 | No |  |  | Contracts in place
3 | Bridge Investigation - Coring Works | Minor Works | TS |  | Investigation |  |  |  |  | 2012-11-21 |  | 2012-11-23 | [6 empty] | A1 Kiwi Cutters & Drillers |  |  |  |  | Contracts in place
4 | Bridge Investigation - Laboratory Testing | Minor Works | TS |  | Investigation |  |  |  |  | 2012-11-30 |  | 2012-12-07 | [6 empty] | OPUS |  |  |  |  | Contracts in place
5 | Labour Hire | Works | GH/RC |  | Early Works | [13 empty] | Various | Various | Yes | Yes
6 | Welder (Labour) | Works | TS | JW | Early Works | [11 empty] | 2013-11-11 | [6 empty] | Parfoot, Puhoi
7 | Earthmoving Plant Hire | Plant Hire | GH/JC |  | Early Works | [11 empty] | 2013-04-16 |  | Heavy Hire NZ | 9501032 | Yes | Yes |  | Contract signed 3/10, plant to mobilised on to site 7/10.
8 | Contract Cartage (Haul Trucks) | Plant Hire | JC/ME |  | Early Works | [11 empty] | 2013-04-04 |  | Gleeson & Cox | 9500442 | Yes | Yes |  | Complete
9 | Plant Float / Low-Loader Hire | Plant Hire | JC |  | Early Works | [11 empty] | 2013-04-16
11 | Crane Hire | Plant Hire | TS | JL | Early Works | 2013-04-17 | 2013-04-15 | 7d | 2013-04-26 | 2013-04-22 |  | 2013-05-03 | 2013-05-03 |  |  |  | 2013-05-06 | 2013-05-06 | NZ Crane Group | 9500136 | Yes | Yes | N
12 | Hiab Hire | Plant Hire | JC/TS |  | Early Works | 2013-04-19 |  | 2w | 2013-05-03 | 2013-04-12 |  | 2013-05-10 | 2013-04-26 | [5 empty] | JC Walker | 9500091 | Yes | Yes |  | Mackenzie, AJ Walker
13 | Vacuum Excavation Hire | Works | HM | DB | Early Works | 2013-04-11 | 2013-04-11 | 4d | 2013-04-15 |  |  | 2013-04-16 | 2013-04-18 |  |  |  | Done |  | Hydrotech | 9500340 | Yes | Yes
14 | Street Sweeper / Road Cleaner Hire | Plant Hire | JC | DC | Early Works | [13 empty] | FH - AKL
15 | Fuel/Diesel Supply | Supply | GH/RC |  | Early Works | [13 empty] | Z Energy | 9500221 | No
16 | Surveyors | Works | ME |  | Early Works | [11 empty] | 2013-03-01 |  | K & N Surveyors | 9500854 | Yes | Yes
17 | Traffic Control | Works | PN/HM |  | Early Works | [11 empty] | Done |  | Action Traffic | 9501089 | Yes | Yes |  | Self perform day works with project owned and operated TMAs
18 | Fencing - Farm type for TAPC | Minor Works | HM |  | Early Works | [11 empty] | Done |  | John Crouch | 9500048 | Yes | Yes
19 | Fencing - 2.4m High for Compound (Design, Supply & Install) | Works | HM |  | Early Works | [11 empty] | Done |  | John Crouch | 9500048 | Yes | Yes
20 | Supply of Site Office Buildings | Supply | HM |  | Early Works | [13 empty] | FH / Portacom | 9500133 | Yes | Yes
22 | Supply of Precast Concrete Barriers (TTM) | Supply | HM |  | Early Works | [11 empty] | Done |  | CSP | Nil
25 | Connection of Services to Site Compound - Electrician | Minor Works | HM |  | Early Works | [11 empty] | Done |  | Peter Brydon | 9500231 | Yes | Yes
26 | Connection of Services to Site Compound - Plumber | Minor Works | HM |  | Early Works | [11 empty] | Done |  | Windybank | 9500241 | Yes | Yes
27 | Pre-Condition Survey Assessment | Minor Works | TS | JL | Early Works | 2013-04-17 | 2013-05-01 |  | 2013-04-26 | 2013-05-07 |  | 2013-05-03 | 2013-05-21 |  |  |  | 2013-05-13 | 2013-05-27 | ACH Consulting | 9500229 | Yes | Yes | N | ACH Consulting
28 | Demolition of Existing Properties | Works | TS | JL | Early Works | 2013-04-17 | 2013-04-23 | 2w | 2013-05-01 | 2013-05-01 |  | 2013-05-10 | 2013-05-23 |  |  |  | 2013-05-20 | 2013-05-27 | Nikau Contractors | 9500248 | Yes | Yes | N | Ward, Nikau
30 | Underboring of Services (if required) | Works | HC |  | Services | [11 empty] | 2014-02-01
33 | Soil Testing | Works | ME |  | Earthworks | [11 empty] | 2013-08-16 | [6 empty] | Recommendation to be finalised
35 | Temporary Works Design - General | Professional Services | TS |  | Design | 2013-07-11 |  | 2w | 2013-07-25 |  | 1w | 2013-08-01 |  | 6w | 2013-09-12 |  | 2013-09-12 |  | ACH Consulting | 9500801 | Yes | Yes
36 | Staging Platform for Bridge Piling - Steelwork | Supply | TS | JL | Structures | 2013-08-12 |  | 1w | 2013-08-19 |  | 1w | 2013-08-26 |  | 3w | 2013-09-16 |  | 2013-09-16 | [6 empty] | Hire from Concrete Structures
41 | Concrete Supply (inc Testing) | Supply | TS |  | Structures | 2013-04-26 | 2013-04-24 | 3w | 2013-05-17 | 2013-05-03 | 2w | 2013-05-31 | 2013-08-05 |  |  |  | 2013-08-26 |  | Allied Concrete | 9500415 | Yes | Yes |  | Allied, Atlas, Stevenson
42 | Reinforcement Supply and fix | Supply | TS |  | Structures | 2013-05-17 | 2013-05-27 | 2w | 2013-05-31 | 2013-06-13 | 1w | 2013-06-07 |  |  |  |  | 2013-08-26 |  | Fletcher Reinforcing | 9500650 | Yes | Yes |  | Fletcher Reinforcing, Steel & Tube, Sim Reinforcing
45 | Stressing Bar Supply | Supply | TS | JL | Structures | 2013-12-14 |  | 2w | 2014-01-11 |  | 1w | 2014-01-18 |  | 1m | 2014-02-15 |  | 2014-02-15 | [6 empty] | Contech, Post Tensioning & Grouting (PT&G)
52 | Concrete Pump Hire | Works | TS | JL | Structures | 2013-06-10 | 2013-07-09 | 2w | 2013-06-24 | 2013-07-17 | 1w | 2013-07-01 |  |  |  |  | 2013-08-27 |  | Pioneer Concrete Pumps | 9500704 | Not signed correctly |  |  | Ian Howe Conc Pumps, Premier Concr Pumping, AAA Pro Pumps
56 | Site Clearance (Vegetaion) | Works | AS |  | Earthworks | [11 empty] | 2013-04-08 |  | Treescape | 9500132 | Yes | Yes |  | Contracts in place
57 | Wick Drain Installation | Works | ME |  | Earthworks | [11 empty] | 2013-08-05 |  | Brian Perry | 9500517 | Yes | Yes |  | Being finalised with BPC
59 | Geotextile / Geogrid Supply | Supply | ME |  | Earthworks | [11 empty] | 2013-08-02
63 | General Fill Supply - Brookby, Whitford and Stephensons | Supply | ME |  | Earthworks | [11 empty] | 2013-08-16 |  | Brookby |  |  |  |  | Brookby setup - others supplies required
64 | Revetment Rock Supply - Winstones | Supply | ME |  | Earthworks | [11 empty] | 2013-08-16 |  | Winstones | 9500736 | No |  |  | Ridge Road / Perrys and Winstones to be setup / VB / Holcim
65 | Woodhill Sand Supply | Supply | ME |  | Earthworks | [11 empty] | 2013-08-30 |  | Woodhill | 9501118 | N/a | N/a |  | Contract and samples required
66 | Lightweight Fill (Pumice Sand) Supply - Winstones | Supply | ME |  | Earthworks | [11 empty] | 2013-08-30 |  | Winstones | 9500736 | No |  |  | Winstones - Pukekawa / Puni
93 | Supply of Steel Barriers for TTM | Supply | HM |  | Early Works | [11 empty] | Done |  | Hiwaycare |  | Yes | Yes
94 | Soil stabilising | Works | HM |  | Early Works | [13 empty] | Hiway Stabilizers | 9500113 | Yes | Yes |  | Hiway Stablisers
95 | Dilapidation/pre-condition survey | Minor Works | AS |  | Early Works
97 | Geotechnical Drilling / Instrumentation | Works | ME |  | Earthworks | [11 empty] | 2013-08-01 |  | McMillans Drilling | 9500712 | Yes | Yes |  | Contractors previously setup as Boaart Longyear
98 | Supply of VCC Instrumentation Equipment | Supply | TS |  | Structures | [11 empty] | 2013-08-20 |  | Advanced Instrument Services | 9500844 | Yes | Yes
99 | Supply of Steel Casings for Piles | Supply | TS | JL | Structures | 2013-09-20 |  | 1w | 2013-09-27 |  | 3d | 2013-09-30 |  | 5w | 2013-11-04 |  | 2013-11-04 | [6 empty] | Asmuss Contract to be negotiated and drafted
100 | Hyrdoseeding for sed control | Works | HM |  | Finishing | [11 empty] | Done |  | Chelsea Landscpes | 9500265 | Yes | Yes
101 | Radio Communications |  | DB | [15 empty] | Team Talk | 9500763 | Yes | Yes |  | Complete
102 | Traffic Management Subcontractor | Works | PN |  | Services | 2013-08-07 |  | 1wk | 2013-08-14 | 2013-08-14 | 1wk | 2013-08-21 | [6 empty] | Action Traffic | 9501089 | Yes | Yes |  | Tender recommendation issued and approved
103 | Machine Guidance Gear | Works | GH | JC | Earthworks | 2013-08-23 |  |  | 2013-08-16 |  | 1 week | 2013-08-23 |  |  |  |  | 2013-09-02 |  | Trimble of Lieca |  |  |  |  | To be finalised this week
104 | Owner Operator - Earthworks | Works | GH | JC | Earthworks | [13 empty] | Luke Glamuzina |  |  |  |  | To be finalised this week
105 | Project Sign | Minor Works | PN |  | Traffic |  |  |  | 2013-09-06 |  | 41525 | [5 empty] | 2013-09-06 |  | Directions
106 | Line Removal - Strip Hog Machine | Works | PN |  | Traffic | [13 empty] | Traffic Systems Ltd
108 | H piles for MSE wall RW4 | Supply | HM | AM
109 | Temporary fencing | Works | HM | DB | [19 empty] | Self Perform - Completed crouch
111 | Line marking - temporary | Works | AS | NO | [14 empty] | Coastline | 9500598 | No
113 | Site boat | Supply | TS / JC
115 | Air Monitoring | Professional Services | BD |  | Services |  |  |  | 2013-09-27 | 2013-09-27 | 41544 | 2013-09-27 | 2013-09-27 |  |  |  | 2013-09-30 | 41547 | Watercare
117 | Percussion Drilling for Wick Drain Obstructions | Works | ME | ME | Earthworks |  |  |  | 2013-10-23 | 2013-10-23 | 41571 | 2013-10-24 | 2013-10-24 |  |  |  | 2013-10-25 | 41572 | Inline Drilling |  |  | Received |  | Procurement required urgently due to plant safety issues with Intorock drilling
119 | Temporary Staging Inspection & Sign-off | Minor Works | TS | JL | Structures | [11 empty] | 2013-11-04 |  | Holmes Consulting Group |  |  |  |  | In conjunction with Temp Staging Supply through Concrete Structures
120 | Install H Piles | Works | HM
122 | Additional Labour Hire | Works | [21 empty] | Completed
123 | site mowing | Works | RC
124 | Ridge Road Quarry material sorting | Works | ME
114 | Permanent Casing Supply | [22 empty] | HJ Asmuss
118 | Timber Pile supply and instalation | Works | ME | ME | [19 empty] | Markovina Piledriving Ltd
121 | Drainage Layer Material | [22 empty] | Holcim
125 | RMD - Equipment | Supply | TS
107 | Historical masonry | Works | AS | NO
110 | Hiab Hire - repricing | Works | HM / JC | [20 empty] | Completed. -ve VO to JC Walker
10 | Barge Hire | Plant Hire | AS |  | Early Works | [13 empty] | Total Marine |  |  |  |  | Action thro Boarts contract
23 | Supply of Anti-Gawk Screens | Supply | HM |  | Early Works | [18 empty] | Not required. Fence to be installed to peds and nothing required EB
24 | Supply of TTM Devices | Supply | PN/HM |  | Early Works | [11 empty] | Done | [6 empty] | Purchased from NMV
31 | Service Relocation | Works | HC |  | Services | [11 empty] | 2013-10-01 | [6 empty] | Not required
34 | Temporary Works Design - Piling Staging | Professional Services | TS |  | Design | [18 empty] | Included with Supply from Fletcher
37 | Staging Platform for Bridge Piling - Decking | Supply | TS |  | Structures | 2013-08-26 |  | 1w | 2013-09-02 |  | 1w | 2013-09-09 |  | 1w | 2013-09-16 |  | 2013-09-16 | [6 empty] | Included as a part of #36
38 | Bored Piling | Works | TS |  | Structures | [18 empty] | Self Perform with FH plant
39 | Pile Trimming - Minor Concrete Demolition | Works | TS |  | Structures | [18 empty] | Self Perform?
40 | Installation of Micro Piles - NO LONGER REQUIRED | Works | TS |  | Structures | [18 empty] | McMillan Drilling Services, Spiral Drillers, Pendletons
43 | Steelfixing - NOT REQUIRED: PART OF SUPPLY PACKAGE | Works | TS |  | Structures | [18 empty] | Fletcher Reinforcing, Steel & Tube, Sim Reinforcing
48 | Delivery of Bridge Beams & Precast Elements - includes delivery | Works | TS |  | Structures | 2013-10-25 |  | 2w | 2013-11-01 |  | 1w | 2013-11-08 |  | 2w | 2013-11-22 |  | 2013-11-25 | [6 empty] | Include as part of Precast Supply Packages #46 & #47
53 | Scaffolding >5m High | Works | TS | JL | Structures | [18 empty] | May not be required
58 | Wick Drain Supply (if not included in Works Contract) | Supply | ME |  | Earthworks | [11 empty] | 2013-05-15 | [6 empty] | Included in subcontract
61 | Subsoil Drain Install (if not self performed) | Works | ME |  | Earthworks | [11 empty] | 2013-09-13
67 | MSE Select Fill Supply | Supply | HM |  | Earthworks | [11 empty] | 2013-10-01 |  | Brookby
69 | Drainage Aggregate Supply | Supply | ME |  | Earthworks | [18 empty] | Cheapest option from above
70 | Testing for Contaminated Material | Minor Works | HM |  | Earthworks | [11 empty] | 2013-09-01
71 | Disposal of Unsuitable/Contaminated Material | Works | HM |  | Earthworks | [11 empty] | 2014-02-01
88 | Streetlighting Supply | Supply | HM |  | Finishing | [11 empty] | 2014-03-17
91 | Site Vehicles (Utes & Vans - OIM?) | Supply | RC |  | P&G
96 | Vibration monitoring | Minor Works | AS |  | Early Works | [18 empty] | Base Line, JP Styles
76 | Supply & Install Noise Wall | Works | TS | AS | Finishing | [11 empty] | 2014-11-01 | [6 empty] | Gibbons, Belaire, Total Infrastructure
49 | Bridge Bearings Supply | Supply | TS | JL | Structures | 2014-05-31 |  | 2w | 2014-06-14 |  | 1w | 2014-06-21 |  | 8w | 2014-08-16 |  | 2014-08-16 | [6 empty] | Pacific Rubber Systems
51 | Timber Supply for Causeway Deck | Supply | TS | JL | Structures | [11 empty] | 2015-07-07 | [6 empty] | Not required until 2015
78 | Sheetpiling | Works | ME |  | Earthworks | [11 empty] | 2013-09-27 | [6 empty] | Is this required?
79 | Supply & Install Permanant Fencing | Works | HM | DB | Finishing | [11 empty] | 2014-02-03
80 | Slipform Concrete Barrier | Works | HM | AM | Finishing | [11 empty] | 2014-03-01
81 | Kerb & Channel | Works | HM | AM | Finishing | [11 empty] | 2014-02-03 | [6 empty] | Msr completed by Harold
82 | Supply of Permanent Precast Concrete Barriers | Supply | ME |  | Finishing | [11 empty] | 2014-02-04 | [6 empty] | Colin Battley - reviewing programme
83 | Supply & Install Guardrail | Works | HM | AM | Finishing | [11 empty] | 2014-03-17 | [6 empty] | John Crouch (SS only), Troy Wheeler (SS & IN)
84 | Supply of Traffic Signs | Supply | ME | PN | Finishing | [11 empty] | 2014-01-29
85 | Supply of Sign Gantries | Supply | HM |  | Finishing | [11 empty] | 2014-08-15
86 | Supply of VMS Gantries | Supply | HC |  | Finishing | [11 empty] | 2015-02-01
87 | Landscaping | Works | BD |  | Finishing | [11 empty] | 2014-05-01
89 | Motorway lighting - Install Lights/Pits & Draw Cables | Works | HC |  | Finishing | [11 empty] | 2014-01-27
92 | Supply of Cathodic Protection System | Supply | TS |  | Structures
112 | GNRI - Temporary Barriers | Variation | AS | [20 empty] | AS/RC/GA - conc barrier requirements for temp layout
116 | Foam Bitumin Stabilised | [22 empty] | FH Waikato
127 | Off site material Storage | Minor Works | [21 empty] | Reliance transport
128 | FH Civil | Works | TS
129 | Concrete Mattress | Works | ME
Formulas:
Tender Package Complete & Issued = [Prices Received]-14
Tender Package Complete & Issued = [Prices Received]-14-14
Prices Received = [Scheduled Date]-7
Scheduled Date = [Scheduled Delivery]-92
Scheduled Delivery = [Date Required on Site]
Tenders Received
Required On Site
Issue Tender
Deliver To Site
Award Contract