NOTE THAT THIS IS A SAMPLE POST SCHEDULE FOR A FILE CAPTURE

AND HD FINISH.

EVERY FILM IS DIFFERENT AND THIS SHOULD NOT BE TAKEN AS

GOSPEL.  THIS IS MEANT ONLY AS A SAMPLE OF THE TYPE OF DETAIL

AND TIME FRAME THAT YOUR FILM MIGHT TAKE.

My 581 Film – The Early Years

Post Production schedule

as of June 1, 2020

John Producer, Producer	(213/987-6543)

Alice Director, Director	(310/210-9876)

Pat Editor, Editor	(323/543-2109)

Wil Post, Post Production Supervisor (888/876-5432)

JUN 29	Shoot video for Sc. 11 playback

JUNE 30	Record music for Sc. 7 playback

Begin editing Sc. 11 playback material

JUL 1	Complete editing Sc. 11 Video playback

JUL 4	INDEPENDENCE DAY (Holiday)

JUL 5-8	Complete video playback Sc. 11

Create video playback tape

JUL 11-13	Complete music playback Sc. 7 Create music playback tape (DA-88)

JUL 15-22	PRODUCTION

JUL 16	Capture Day 1 pix files and sound dailies to Editor drive

Sync dailies

JUL 17	Capture Day 2 pix files and sound dailies to Editor drive

DVD of Day 1 dailies to director

Sync dailies

JUL 18	Capture Day 3 pix files and sound dailies to Editor drive

DVD of Day 2 dailies to director

Sync dailies

JUL 19	Capture Day 4 pix files and sound dailies to Editor drive

DVD of Day 3 dailies to director

Sync dailies

Begin editing

My 581 Film – Post Sked	Page 1	as of 6/1/2020

JUL 20	Capture Day 5 pix files and sound dailies to Editor drive

DVD of Day 4 dailies to director

Sync dailies

JUL 21	Capture Day 6 pix files and sound dailies to Editor drive

DVD of Day 5 dailies to director

Sync dailies

JUL 22	Capture Day 7 pix files and sound dailies to Editor drive

DVD of Day 6 dailies to director

Sync dailies

JUL 23	Capture Day 8 pix files and sound dailies to Editor drive

DVD of Day 7 dailies to director

Sync dailies

JUL 24	DVD of Day 8 dailies to director Finish synching dailies

JULY 25-31	Director out of town.

AUG 7	Screen Editor’s Cut (Cut #1) Director/Producer give feedback Output cut for Director

AUG 8 – 21	Post Building Closed

Director screens dailies, gives notes

Editor/Director meet several times

Begin assembling titles list

Search for composer begins

AUG 22	Director’s Cut (Cut #2) begins (4 weeks) Start compiling production book

SEP 5	LABOR DAY (Post Closed)

SEP 6	Internal screening for Editor/Director

SEP 16	Screen Cut #2 (director/producer/mentor)

SEP 17	Begin Cut #3 (3 weeks)

SEP 12	Continue titles search and production book

SEP 19	Interview Composers/Collect demos

SEP 26	Continue Cut #3

My 581 Film – Post Sked	Page 2	as of 6/1/2020

OCT 7	Screen Cut #3

Lock in Credit Lists for production Lock Sound Designer

OCT 10	Begin Cut #4 (2 weeks)

OCT 17	VFX for Scene 15 to VFX house.

OCT 24	Screen Cut #4

Start planning Pick-ups

OCT 25	Begin 5th  Cut (2 weeks)

Get Approval on credits from mentor and

faculty

Lock Composer

OCT 31	Halloween

NOV 7	Screen Cut #5 (Composer attends)

Begin planning sound design.

1st  pass on VFX for Scene 15

NOV 8	Start 6th  Cut (1-1/2 weeks)

Begin assembling pickup list

VFX for Scene 10 to VFX house.

NOV 18	Screen Cut #6 (Public Preview with civilians)

NOV 19	Begin Cut #7. (two weeks) Editor makes tweaks

pre-pick-ups

NOV 23-26	THANKSGIVING BREAK (Editor and Director out

of town)

NOV 27	Continue 7th  Cut

Prep pickups

Receive 2nd  pass on Scene 15 VFX

Receive 1st  pass on Scene 10 VFX

NOV 29	Shoot Pickups

NOV 30	Ingest pickups

Temp SFX from Sound Designer

Temp music from Composer

DEC 2	Final pass on Scene 15 VFX

2nd pass on Scene 10 VFX

DEC 3	Screen Cut #7 (with pickups and new VFX)

DEC 5	Begin Cut #8 (1-1/2 weeks)

DEC 10	Add Sound Desginer’s temp SFX

My 581 Film – Post Sked	Page 3	as of 6/1/2020

Include composer’s temp music

DEC 12	Screen Cut #8

DEC 12-14	Final tweaks. (9th  Cut)

Final pass on Scene 10 VFX

DEC 15	Screen FINAL CUT (Cut #9)

DEC 16	PICTURE LOCK (8th  Cut)

QT files for sound and music

AAFs for sound

Project files and EDLs created for online

DEC 17	Spotting session for music

Begin opticals

DEC 18	Spotting session for sound

Composer starts writing to picture

DEC 19	Sound designer begins editing

BGs/Dialogue/FXs

Dialgoue editor works

Preliminary ADR list delivered

DEC 20- JAN 8  Winter break

Composer plays themes for director

JAN 9	Resume dialogue and effects editing

Schedule warnings with actors for ADR

JAN 16	MARTIN LUTHER KING DAY (HOLIDAY)

JAN 20	ADR List due.	Begin booking actors

Begin finalizing credits

JAN 23-27	Foley decisions/ Schedule Foley artists

Composer writes

JAN 30	FOLEY Session

Composer writes

FEB 6-10	ADR

Arrange recording session/Find musicians

FEB 10	Lock credits list

FEB 13	Credits to titles designer

DVD art elements and label designer starts DVD text elements writing

FEB 20	PRESIDENTS DAY (Holiday)

My 581 Film – Post Sked	Page 4	as of 6/1/2020

FEB 27	Record music

Delivery of titles elements.

MAR 1	Online/Color Correction/DI

Create video assets for DVD Authoring

MAR 2	Outputs from online

Revised QTs sent to sound.

MAR 6-10	Pre-mixes

Finish image assets for DVD

MAR 13-18	Spring Break

MAR 20-21	FINAL MIX

MAR 22	Create stereo and 5.1 elements.

Create audio assets for DVD.

MAR 23	Layback.

MAR 24	Test screen finished film

APR 3	Finish production book

APR 10	Screen for mentor

Start dubs

Begin DVD Authoring

APR 24	Complete DVD Authoring

Begin DVD Replication (???)

My 581 Film – Post Sked	Page 5	as of 6/1/2020